## Kanban Board
To Do
In Progress
Done
|  | To Do | In Progress ...(enter maximum tasks in flow below) | Done
4
User Stories | State
as a user, I want to search for a book by Title, Author, ISBN | To Do | Search for a book
as a user, I want to check out a book | To Do | User is able to check out book if available and updates database
as a librarian, check out a book |  | Librarian records checkout and updates who has it
as a librarian, I want to turn a book back in | To Do | Code registration. [WX, YZ]
as a user, I want to turn a book back in | To Do | If the user has an online version, check it in. System will delete access to online book
as a librarian, add new books | To Do | Add new books to inventory
as a librarian, remove a book from the system | To Do | Remove a book from inventory
as a librarian, need to modify book inventory | To Do | Modify book
as a librarian, need to update (modfiy) book inventory to update the book edition | To Do | Update edition
as a librarian, list all the books I have | To Do | List all books online
as a librarian, list all the books that are lent out and who has them | To Do | List all books checked out including who has them
as a librarian, print a list of books and if they are lent out, list who has them | To Do | Hardcopy print of all books and who has them if checked out
as a librariran,have full access | To Do | Give full acess to librarians
as an user, I should be able to search and checkout online books only | To Do | Give limit access to user to search and checkout online books
as a librarian, add a new user | To Do | Add a new user
as a librarian, remove a user | To Do | remove a user
as a librarian, modfiy user info | To Do | Modify a user
as a programmer, create book table | To Do | Create a table for books
as a programmer, create author table | To Do | Create a table for authors
as a programmer, add permissions for user and librarian | To Do | Create permissions
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
0 | To Do
Note on A4: User Stories from the sheet, "Sprint Backlog".
Note on B4: States of tasks pertaining to the stories. Choose one of three states from the dropdown list.
Note on D5: Enter the maximum number of tasks your team should be handling on any one day.

## Sprint Backlog
User Stories | Tasks | Owner(s) | Remaining hours at the Beginning of day:
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
|  |  | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
|  |  | 10 | 8 | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EXAMPLE: As a website customer, I need to be able to register so as to be able to gain access. | Make registration screen. | AB, CD, EF | Remaining hours at the Beginning of day: 1: 10; Remaining hours at the Beginning of day: 2: 8; Remaining hours at the Beginning of day: 3: 5; Remaining hours at the Beginning of day: 4: 6
| Design registration logic. | PQ
| Code registration. | WX, YZ
| Test registration. | AB, CD, EF
EXAMPLE: As a website customer, I would like to see my account profile , to be well prepared. | Make profile screen. | PQ
| Design profile logic. | WX, YZ
| Code profile. | AB, CD, EF
| Test profile. | PQ
EXAMPLE: As a website customer, I must get daily alerts to remain informed. | List alerts.
Code alerts
Test alerts
Test profile.
EXAMPLE: A project manager alerts team on late tasks | Alert interface
Send alert via email
Alert RSS
Note on A1: While entering a story, you should use the dropdown list which shows stories assigned to this track.
Note on B1: Tasks pertaining to the stories.
Note on C1: Initials of task owners.
Note on E4: Remaining hours at the beginning of the (numbered) days. (Do not enter in the blue area).

## User Stories
Product Backlog spreadsheet-key:
| Track name: | Track 1
Priority | Track | User Stories | Story Points | Acceptance Tests | Acceptance Tests | Acceptance Tests | Acceptance Tests | Acceptance Tests | Acceptance Tests | Acceptance Tests | Acceptance Tests | User Stories for the Track
#N/A
Note on B1: If the Product Backlog URL is, "https://spreadsheets.google.com/ccc?key=tV8ZAvuDy93jSKXXrKrb0tQ&hl=en#gid=1", the spreadsheet-key is the text between 'key=' and '#', i.e., "tV8ZAvuDy93jSKXXrKrb0tQ&hl=en".
Note on B2: The name of this track. It should match one in the Product Backlog.
Note on A3: Priority of the User Stories.
Note on B3: Track to which the story is assigned.
Note on C3: User Stories, i.e. concise requirement statements.
Note on D3: Relative size of the story.
Note on E3: Short statement of acceptance test.

## Burndown Chart
Beginning of day | Planned remaining hr | Actual remaining hr
1 | 10 | 10
2 | 9 | 8
3 | 8 | 5
4 | 7 | 6
5 | 6 | 0
6 | 5 | 0
7 | 4 | 0
8 | 3 | 0
9 | 2 | 0
10 | 1 | 0
11 | 0 | 0

## Instructions
How to use this template
Authored by Paradigm PoP, LLC.
Check out ScrumPoP - our agile tool which uses this template.
This is a template to create a Sprint Backlog (prioritized list of requirements, generally in the form of User Stories). Sprint Backlogs are typically used in agile project iterations (Sprints, 2wk long are supported). This template is capable of connecting to the "Product Backlog" template available from us (Paradigm PoP / mypopproject) on Google Templates. Both templates are used in the cloud based tool published by Paradigm PoP, called "ScrumPoP". It provides active project management and collaboration for agile teams.
Set up
1 | Go to "File/ Rename..." and rename the template to something like, "YourProjectName - Sprint Backlog".
2 | [Skip this if you do not use the Google template of Product Backlog published by us (or do not plan to connect to it).] [A] in the sheet, "User Stories", insert the "Product Backlog spreadsheet-key" (if the Product Backlog URL is, "https://spreadsheets.google.com/ccc?key=tV8ZAvuDy93jSKXXrKrb0tQ&hl=en#gid=1", the spreadsheet-key is the text betweeen 'key=' and '#', i.e., "tV8ZAvuDy93jSKXXrKrb0tQ&hl=en"), [B] Enter the "Track name" for the track your team is supporting, e.g. "Track 1". It should match the track name entered for your track in the Product Backlog. This Sprint Backlog will then show all User Stories from the Product Backlog (incl. their acceptance tests). In the sheet, "Sprint Backlog", it will help you see the subset of stories assigned to this track.
3 | In the sheet, "Kanban Board", enter maximum tasks in flow that you would like to be alerted for, within the column, "In Progress...".
Use
1 | Add User Stories to the sheet (ref. examples), "Sprint Backlog". If you use the Product Backlog shared by us on Google templates and have set up this backlog as above, you can use the dropdown list which will show the stories subset within the Product Backlog, for your track. You should then choose one of those stories.
2 | In the sheet, "Sprint Backlog", add tasks for each story. Add task owner initials. Have the owners enter remaining hours per day.
3 | The sheet, "Burndown Chart" will show a chart of "Total remaining hr" (both, expected - based on the value entered for the first day, and actual), at the beginning of each day.
4 | The sheet, "Kanban Board" will show the tasks (with owner initials). Have the owners change their state regularly (To Do / In Progress / Done as will appear on a dropdown list). The tasks will move to the appropriate column and change color. When the number of tasks in flow exceeds your preset maximum value, the "In Progress..." column will flag this with a red heading color. For the tasks marked "In Progress", when you refer to the the sheet, "Sprint Backlog", a yellow "hr ?" alert will appear - reminding the team to input remaining hours.
© 2010 Paradigm PoP LLC